## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-CN-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1461 |  |  | Transmital Date: 10/8/2022
Document Title: Calculation Note For Depressurizing (Min. Design Temperature ) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1461 |  |  | Transmital Date: 10/8/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص تغییرات عمده در پارامتر فشار نهایی ، لازم است دمای کمینه سیال در ظروف و شیرها و همچنین مقدار Peak Flow محاسبه شده برای شیرهای BDV نسبت به نسخه قبلی مدرک ، فایل Native محاسبات برای این امور ارسال گردد. |  | 1401-2294-323351 | 1401/09/01 | فایل محاسباتی Native در تمامی ویرایش های مدرک فوق به آن کارفرمای محترم ارسال شده است.
2 | نام شیرهای BDV-2131 A/B/C ( بعد از V-2102) در مدرک P&ID با اطلاعات مندرج در مدرک میبایست مورد بررسی مجدد و مطابقت قرار گیرد. |  | 1401-2294-323351 | 1401/09/01 | اصلاح گردید.
3 | در جدول شماره یک ، بخش 8، در ستون تجهیزات اصلی و خطوط لوله بخش مربوط به BDV-2131 ، شماره سریال خط مربوط به GAS-111-0041-CS00-6”-PT مطابق با آخرین مدرک P&ID می بایست مورد بررسی و اصلاح قرار گیرد. |  | 1401-2294-323351 | 1401/09/01 | اصلاح گردید.
4 | با توجه به افزایش حجم تخلیه توسط شیر XV-2110 نسبت به نسخه قبل و ثابت ماندن زمان تخلیه ، علت کاهش Peak Flow و سایز RO می بایست اعلام شود. |  | 1401-2294-323351 | 1401/09/01 | افزایش حجم v-2104 نسبت به ویرایش قبل سبب تغییر مذکور می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021