## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1461 |  |  | Transmital Date: 10/8/2022
Document Title: Flare Radiation & Dispersion Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1461 |  |  | Transmital Date: 10/8/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص ارتفاع فلر در پاراگراف 5 بند 4,1 می بایست توضیحات مورد بررسی و اصلاح قرار گیرد. |  | 1401-2294-323351 | 2022-11-22 | اصلاح گردید.
2 | در خصوص مبنای ترکیب درصد اجزاء استفاده شده در سناریوهای Fire Area 1 می بایست بیان شده و در صورت انجام شبیه سازی ، فایل مربوط برای این امور ارسال گردد. |  | 1401-2294-323351 | 2022-11-22 | ترکیب درصد گاز خروجی از فلر بر اساس سناریو FIRE CASE 1 که در مدرک Flare Network Study Report به شماره مدرک "BK-GCS-PEDCO-120-PR-RT-0001" در نظر گرفته شده است.
3 | در خصوص دمای ذکر شده برای سیال ورودی فلر، می بایست مجدد مورد بررسی قرار گیرد. |  | 1401-2294-323351 | 2022-11-22 | دمای سیال ورودی به فلر بر اساس ساس سناریو FIRE CASE 1 که در مدرک Flare Network Study Report به شماره مدرک "BK-GCS-PEDCO-120-PR-RT-0001" در نظر گرفته شده است.
4 | در خصوص تأثیر زیاد F-FACTOR در ارتفاع فلر،لازم است توضیحات لازم در خصوص تغییر فرضیه چهارم در بند 4,4 ارایه گردد. |  | 1401-2294-323351 | 2022-11-22 | اعمال گردید.
5 | در خصوص عبارت Flare Thermal Radiation در ستون مربوط به سرعت باد می بایست مورد بررسی و حذف قرار گیرد. |  | 1401-2294-323351 | 2022-11-22 | با توجه به بند 10-7 مدرک PROCESS BASIS OF DESIGN به شماره مدرک "BK-GNRAL-PEDCO-000-PR-DB-0001" ، میزان Flare Thermal Radiation برابر با 10 M/S در نظر گرفته شده است.
6 | درخصوص فشار اتمسفریک، مطابق مدرک DESIGN BASIC می بایست مورد بررسی و اصلاح قرار گیرد. |  | 1401-2294-323351 | 2022-11-22 | اصلاح گردید.
7 | لازم است توضیحات لازم در خصوص اطلاعات درج شده در جدول 7 قسمت 6,1 ارایه گردد. |  | 1401-2294-323351 | 2022-11-22 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021