## CRS
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1461 |  |  | Transmital Date: 10/8/2022
Document Title: Flare Radiation & Dispersion Study Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1461 |  |  | Transmital Date: 10/8/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-RT-0002-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس مفاد صورتجلسه مورخ 1401/08/07 در خصوص مدارک مرتبط با شبکه فلر، اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06006 | 2022-10-29 | اعمال گردید
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06006 | 2022-10-29 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 29/10/2022 |  |  |  |  | Date: