## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0024 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1265 |  |  | Transmital Date: 8/10/2022
Document Title:Process Data Sheets For Sump Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1265 |  |  | Transmital Date: 8/10/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0024_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مشخصات فرآیندی سیال، معضلات تعمیراتی و اسناد پیمان، پمپ Sump Pump می بایست بصورت افقی در نظر گرفته شود یا دلایل فنی قابل دفاع ارایه گردد. |  | 1401-2294-238226 | 1401/07/05 | اصولا برای پمپ های تخلیه چاله به دلیل مشکلات NPSH از پمپ های Submerged و یا عمودی استفاده می گردد. ضمن اینکه در پلات پلن اسناد پایه نیز به درستی از پمپ عمودی برای این سرویس بهره برده شده بود
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: