## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-CV-CN-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1435 |  |  | Transmital Date: 24-SEP-2022
Document Title: Calculation Note For Flood Control |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1435 |  |  | Transmital Date: 24-SEP-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-CV-CN-0001-D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نمای شماتیک دهانه کالورت در بخش تعیین خط پروژه (صفحه 33) مطابق با مدارک پیمان نمی باشد. لذا مورد تایید نیست. اصلاح گردد. |  | 01/2294/260525 | 1401/07/20 | اصلاح شد. همانطور که در متن مدرک آوره شده است، این شکل شماتیک بوده و به جهت معرفی پارامترهای مورد استفاده در محاسبات، آورده شده است و بدیهی است که نقشه های اجرایی مطابق استانداردهای ارائه شده(Standard Drawing For Culvert & Details)، اجرا خواهند گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: