## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1310 |  |  | Transmital Date: 8/24/2022
Document Title: Calculation Note For Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1310 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است مقصد جریان ارسالی پمپ های P-2101 در شماتیک اصلاح گردد. |  | 1401-2294-271653 | 1401/07/27 | اصلاح گردید.
2 | آیتم شماره 2 "Max Liquid Level in Drum" برای پمپ P-2202 مطابق آخرین P&ID و سایزینگ ارسالی نمی باشد و باید اصلاح گردد. |  | 1401-2294-271653 | 1401/07/27 | اصلاح گردید.
3 | آیتم شماره 19 "Shut off Pressure" برای پمپ P-2104 مطابق با معیارهای ذکر شده(فشار طراحی v-2107 + اختلاف فشار پمپ) در مدرک Process Design Criteria میبایست مورد بازنگری قرار گیرد. |  | 1401-2294-271653 | 1401/07/27 | مورد بازنگری قرار گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: