## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1195 |  |  | Transmital Date: 7/26/2022
Document Title: Process Data Sheets For Diesel Oil Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1195 |  |  | Transmital Date: 7/26/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0007_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است Tag No. مندرج در داده برگ فرآیندی V-2206 به صورت مشخص برای هر یک از احجام با عناوین: V-2206 A (Fire Water Diesel Oil Drum) V-2206 B (Diesel Generator Diesel Oil Drum) قید گردد. |  | 1401-2294-219178 | 1401/06/20 | با توجه به آخرین توافقات و تصمیمات اتخاذ شده یک مخزن DIESEL مطابق با ابعاد طراحی پایه در نظر گرفته شده است و تغییرات لازم در داده برگ فرآیندی اعمال گردیده است.
2 | Liquid Level های مندرج در شماتیک های مربوط به داده برگ فرآیندی V-2206 A/B با آخرین مدارک "Calculation Note For Drum Sizing" و P&ID مطابقت ندارد.لازم به ذکر است HLL مندرج در شماتیک تجهیزات مذکور از قطر آنها بیشتر می باشد. |  | 1401-2294-219178 | 1401/06/20 | اصلاح گردید.
3 | لازم است نظرات این امور در خصوص V-2206 A/B بروی مدرک: "Calculation Note For Drum Sizing -D04 " در داده برگ فرآیندی مربوطه اعمال گردد. |  | 1401-2294-219178 | 1401/06/20 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: