## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1195 |  |  | Transmital Date: 26/07/2022
Document Title: Process Data Sheets For Diesel Oil Drum |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1195 |  |  | Transmital Date:26/07/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-DT-0007-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت "min" در شماتيك ارائه شده مبهم است. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | عبارت حذف گردید
2 | نازل MW هم در شماتيك و هم در PID مربوطه نشان داده شود. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | نازل M همان نازل MW می باشد.
3 | ارتفاع سيال در شماتيك 2 متر لحاظ شده در صورتي كه قطر مخزن 1.2 متر است. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | شماتیک و ارتفاع مخزن بازبینی گردید.
4 | ارتفاع مخزن با P&ID مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | اصلاح گردید.
5 | نقطه نظرات ارائه شده در سايزينگ ظروف، در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | اعمال گردید.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05410 | 2022-08-13 | مورد توجه قرار می گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: | Signature
| Date: 13/08/2022 |  |  |  |  | Date: