## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-CN-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1171 |  |  | Transmital Date: 19/Jul/2022
Document Title: HVAC Calculation Note For Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-HV-TR-1171 |  |  | Transmital Date: 19/Jul/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-HV-CN-0001-D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | air conditioned for Battery room shall considered.(Table of item 5 shall revised and other data for battery room shall added) |  | BK-SUR-ENG-HVC-01-06424 | 2022-12-18 | According to Basics of Project Design, temperature control of Battery room is not needed.
2 | calaculation load shall issued firstly or along with other subsequent documents. |  | BK-SUR-ENG-HVC-01-06424 | 2022-12-18 | It Has Done.
3 | HAP repot shall including of air system input. |  | BK-SUR-ENG-HVC-01-06424 | 2022-12-18 | It Has Done.
4 | After applying the changes , Don't rev. up and replace this document |  | BK-SUR-ENG-HVC-01-06424 | 2022-12-18 | It Has Done.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:12/18/2022 |  |  |  |  | Date: