## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1310 |  |  | Transmital Date:8/24/2022
Document Title:P&ID - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1310 |  |  | Transmital Date:8/24/2022
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سایز شیرهای کنترلی در نظر گرفته شده برای موقعیت های جدید چاه های موجود هم خوانی نداشته و مورد تایید نمی باشد. |  | 1401-2294-271653 | 1401/07/27 | سایز کنترل ولو ها پس از دریافت اطلاعات نهایی از سازنده در مدارک اعمال خواهد شد. لازم به ذکر است این پیمانکار بر اساس اطلاعات سیال خطوط جریانی میزان Cv را محاسبه نموده و در مدرک CALCULATION BOOK FOR (CV,PSV,PUMP&LINE SIZING) به شماره مدرک "BK-W007S-PEDCO-110-PR-CN-0001" ارائه نموده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021