## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-CV-PY-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1576 |  |  | Transmital Date: 11/6/2022
Document Title: Civil and Structural drawings -W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1576 |  |  | Transmital Date: 11/6/2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-CV-PY-0002-D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح گردید.
2 |  |  | 1401-2294-338405 | 1401/09/10 | ریفر داده شد
3 |  |  | 1401-2294-338405 | 1401/09/10 | حذف گردید
4 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح گردید.
5 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح گردید.
6 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح شد
7 |  |  | 1401-2294-338405 | 1401/09/10 | عرض کانال ضلع جنوبی پد بتنی به درخواست شرکت محترم پترو ایران، بدلیل جمع آوری آب‌های سطحی کل پد بتنی، از 30 سانتی متر به 70 سانتی متر افزایش یافته است.
8 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح شد
9 |  |  | 1401-2294-338405 | 1401/09/10 | اضافه شد
10 |  |  | 1401-2294-338405 | 1401/09/10 | حذف گردید
11 |  |  | 1401-2294-338405 | 1401/09/10 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: