## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1216 |  |  | Transmital Date: 7/30/2022
Document Title: Calculation Note For Control Valve Sizing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1216 |  |  | Transmital Date: 7/30/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درصد بازشدگي شير 2102 براي دبي نرمال مطابق Criteria اصلاح گردد. |  | BK-SUR-ENG-PCS-01-05440 | 2022-08-14 | با توجه به نامه شماره 01/2294/205792 مورخ 1401/06/10 در محاسبات Cv شیرهای کنترلی ارائه شده و سایر موارد طراحی ازجمله درصد بازشدگی پس از دریافت اطلاعات نهایی از سازنده اعمال می گردد.
2 | مقادير CV در جدول 5.3 با محاسبات صورت گرفته مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-05440 | 2022-08-14 | اصلاح گردید.
3 | در خصوص شير 2135 و 2152 پيشنهاد مي گردد فشار خروجي بر اساس بيشترين فشار محتمل شبكه فلر محاسبه گردد. |  | BK-SUR-ENG-PCS-01-05440 | 2022-08-14 | فشار خروجی شیر های 2135 و 2152 بر اساس بدترین سناریو شبکه فلر در نظر گرفته شده است.
4 | لازم است محاسبات مربوطه پس از انتخاب سازنده، توسط سازنده نيز مجددا صورت پذيرد. |  | BK-SUR-ENG-PCS-01-05440 | 2022-08-14 | اعمال می گردد.
5 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05440 | 2022-08-14 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: