## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-CN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1251 |  |  | Transmital Date: 06/AUG/2022
Document Title: Calculation Note For Pipeline Wall Thickness |  |  |  |  | PEDCO Tr. No.: BK=PEDCO-NISOC-0005-PL-TR-1251 |  |  | Transmital Date: 06/AUG/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D02 |  |  | CRS Status: | C1
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صورتي كه كاهش ضخامت خطوط لوله 8 اينچ گاز و 4 اينچ كاندنسيت نسبت به مهندسي پايه مورد تأييد ذينفع اصلي پروژه قرار گيرد نقطه نظر خاصي مطرح نمي باشد. در صورت تأييد ذينفع اصلي پروژه نسخه AFC ارسال گردد. |  | BK-SUR-ENG-PPL-01-05442 | 2022-08-15 | احتراما پیرو کامنت کارفرمای محترم در مدرک BK-PPL-PEDCO-320-PL-SP-0001 ضخامت خط لوله 8 اینچ گاز اصلاح شد.
2 | مطابق نظر ذينفع اصلي در بخش 3.1 ويرايش 3 براي استاندارد IPS-M-PI-190 درج گردد. |  | BK-SUR-ENG-PPL-01-05442 | 2022-08-15 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 15/08/2022 |  |  |  |  | Date: 15/08/2022