## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-SP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1465 |  |  | Transmital Date: 08.OCT.2022
Document Title: Pipeline Material Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-1465 |  |  | Transmital Date: 08.OCT.2022
CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PL-SP-0001_D03
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | -همانگونه که در جلسه پیشرفت پروژه مورخ 17/07/1401 بیان گردید و مجددا در جلسه مورخ 01/08/1401 نیز تاکید شد ضروری است پیمانکار مشخصات خط لوله مذکور را مطابق با اسناد پایه در نظر گرفته و از بروز تاخیرات بیش از پیش در این زمینه جلوگیری نماید. از این رو مشخصات مندرج در این مدرک مورد تایید نبوده و می بایست در اسرع وقت اصلاح گردد. |  | 01-2294-279785 | 1401/08/03 | ضخامت انتخاب شده براساس نتایج محاسبات بود که قبلا به تایید آن کارفرمای محترم رسیده بود. علیرغم آن براساس دستور آن کارفرما ، مشخصات خط لوله مذکور مطابق با اسناد پایه بازبینی گردید و نقطه نظر اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 14/03/2022 |  |  |  |  | Date: 14/03/2022