## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PH-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0612 |  |  | Transmital Date: 2/20/2022
Document Title: Control Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0612 |  |  | Transmital Date: 2/20/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PH-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نحوه کنترل و عملکرد کمپرسورها به طور کامل شرح داده شود. |  | 1400-2294-445277 | 1400/12/21 | با توجه به مدارک P&ID و سایر مدارک مرتبط، بخش کنترل و ابزار دقیق کمپرسورها بر عهده سازنده بوده و همانطور که که در مدرک قید گردیده است پس از دریافت اطلاعات تکمیلی از سازنده در مدرک مذکور نیز اعمال می گردد.
2 | در توضیحات بخش 4-7 مدرک CONTROL PHILOSOPHY دو مرتبه نام کولر هوایی AE-2101 درج شده و می بایست یکی از آن ها به AE-2102 تغییر یابد |  | 1400-2294-447187 | 1400/12/22 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: