## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-PY-0004_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1505 |  |  | Transmital Date: 17-Oct-2022
Document Title: Lighting & Small Power Layout For Switchgear Building of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-EL-TR-1505 |  |  | Transmital Date: 17-Oct-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0004_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه اینکه مدرک محاسبات روشنایی محوطه سر چاهی، تاکنون نهایی نشده و Commented می باشد مقتضی است، پس از تایید مدرک مذکور این مدرک مطابق با آن اصلاح و مجددا برای این امور ارسال گردد. |  | 1401-2294-294097 | 1401-08-12 | مدرک محاسبات روشنایی بر اساس نامه شماره 280865 آن کارفرمای محترم مورد ویرایش قرار گرفته و ارسال می گردد. بر همین اساس نیز مدرک جانمایی روشنایی تغییر پیدا نموده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Sadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 31-Oct-22 |  |  |  |  | Date: