## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W035-PEDCO-110-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1474 |  |  | Transmital Date: 10/10/2022
Document Title: Process Data Sheets For Instrument Devices - W035 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1474 |  |  | Transmital Date:10/10/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W035-PEDCO-110-PR-DT-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بخش فرآیند بر روی داده برگ تجهیزات ابزار دقیق ارائه خواهد شد. در خصوص این مدرک صرفا لازم است نقطه نظرات ذینفع اصلی پروژه اعمال گردد. |  | BK-SUR-ENG-PCS-01-06054 | 2022-11-01 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 30/10/2022 |  |  |  |  | Date: