## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0809 |  |  | Transmital Date:4/12/2022
Document Title: Relief Load Summary |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0809 |  |  | Transmital Date:4/12/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه BK-PEDCO-NISOC-0101-PR-LT-1290 مورخ 1401/01/24 (شماره سیستمی 1225) با موضوع صرالذکر ، لازم است مبانی محاسبات سناریوهای FIRE CASE با جزئیات ذکر شده و برای هر شیر PSV سناریوی BLOCKED OUTLET در نظر گرفته شده و نتایج محاسبات ارائه گردد. |  | 1401-2294-55025 | 1401/02/19 | با توجه به طراحی پایه و سناریو آن در خصوص PSV SIZING از منظر این پیمانکار احتمال وقوع CASE BLOKED OUTLET وجود نخواهد داشت .لازم به ذکر است توپک رانی یک عملیات Intermittent بوده و احتمال بسته شدن ولو در زمان انجام عملیات بسیار ناچیز است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021