## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PR-PH-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0921 |  |  | Transmital Date: 09.May.2022
Document Title: Control Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0921 |  |  | Transmital Date: 09.May.2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-PR-PH-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاراگراف دوم بند 4،2 PIC-1001 A/F ،Tag Number با مدرک P&ID مغایرت داشته و باید تصحیح گردد. |  | 01/2294/100891 | 1401/03/23 | در مدرم فوق اشاره ای به PIC نشده است و در پاراگراف دوم بند 4،2 FIC-1007 A/F ،Tag Number بر اساس مدرک P&ID اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021