## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0809 |  |  | Transmital Date:4/12/2022
Document Title: Relief Load Summary |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0809 |  |  | Transmital Date:4/12/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار طراحي با P&ID مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | اصلاح گردید.
2 | اطلاعات فرايندي همچون دما با توجه به Case مطرح شده صحيح نمي باشد. |  | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | اصلاح گردید.
3 | درنظر گرفتن Fire Case براي توپكران و توپكگير نيازمند شفاف سازي از طرف پيمانكار مي باشد. |  | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | براساس مدارک طراحی پایه برای تجهیزات pig launcher , pig receiver شیر psv درنظر گرفته شده است.با توجه به standard drawing ارسالی از طرف خود کارفرما و تجربیات این پیمانکار پیشنهاد می گردد به جای psv از TSV استفاده شود .در صورتی که کارفرما با نصب شیر TSV موافق باشد ، مراتب را امر به ابلاغ می فرماید .
4 | ضروريست است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-04095 | 2022-04-30 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021