## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-RT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0791 |  |  | Transmital Date: 09/APR/2022
Document Title: PDMS Model Review Report (30%) - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0791 |  |  | Transmital Date:09/APR/2022
[5 empty] | CRS No:CRS-BK-W007S-PEDCO-110-PI-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علیرغم در ج صورتجلسه بازدید میدانی در مدرک (صورتجلسه مورخ 1400/12/15 منضم به نامه به شماره 00/2294/443041 ) موارد مندرج در بخش 6 مدرک با توافقات صورت گرفته مغایرت دارد . لذا مدرک مجددا اصلاح و بازنگری گردد. |  | 01/2294/20714 | 1401/01/23 | مدل 60 % برهمان اساس بازنگری و ارسال گردید و گزارش آن جلسه نیز در قالب مدرک ارسال گردیده و به تایید آن کارفرمای محترم رسیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 16/04/2022 |  |  |  |  | Date: 16/04/2022