## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-RT-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0741 |  |  | Transmital Date:26-Mar-2022
Document Title: PDMS Model Review Report (30%) - GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0741 |  |  | Transmital Date:26-Mar-2022
[5 empty] | CRS No:CRS-BK-GCS-PEDCO-120-PI-RT-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | گزارش بررسي مدل سه بعدي بايستي همراه با فايل Native مدل سه بعدي با قابليت اجرا بر روي نرم افزار NAVIS 5 ارائه گردد. |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | در بازبینی های بعدی ارائه می گردد.
2 | در عنوان مدرك GCS اضافه گردد تا مشخص باشد كه مربوط به New Gas Compressor station مي باشد. |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | اضافه گردید.
3 | در بخش 6.0 مدرك تاريخ جلسه بررسي مدل به 1400/12/01 اصلاح گردد. |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | اعمال گردید.
4 | در مدرك جدول چك ليست براي مرحله 30% مطابق مدرك 3D-Model (PDMS) Review Procedure ارائه شده و نتيجه بررسي و نقطه نظرات ارائه شده درج گردد. |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | در جلسه مذکور تمامی موارد مندرج در چک لیست بررسی و نهایی گردیده است و اضافه نمودن این جدول ، احتمالا با عث بروز سردرگمی و یا شاید نقطه نظرات جدید واحدهای مختلف ذینفع اصلی گردد.
5 | صورتجلسه بررسي مدل سه بعدي مورخ 1400/12/01 پيوست مدرك گردد و موارد ذكر شده در بخش 6.0 مطابق صورتجلسه باشد. |  | BK-SUR-ENG-PIP-01-03858 | 2022-04-11 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 11-Apr-2022 |  |  |  |  | Date: 11-Apr-2022