## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-RT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0791 |  |  | Transmital Date: 09/APR/2022
Document Title: PDMS Model Review Report (30%) - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0791 |  |  | Transmital Date:09/APR/2022
[5 empty] | CRS No:CRS-BK-W007S-PEDCO-110-PI-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ابتدا بايستي Plot Plan منيفولد بر اساس صورتجلسه توسعه فنس كلاستر بينك مورخ 1400/12/15 نهايي گردد سپس مدل سه بعدي ارائه گردد. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | پلات پلن ارائه گردیده است.
2 | مطابق صورتجلسه مورخ 1400/12/15 حداقل عرض جاده دسترسي كنار فنس بايستي 5 متر در نظر گرفته شود. عرض مفيد جاده دسترسي در مدل 4 متر در نظر گرفته شده است |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | در نظر گرفته شده است.
3 | اصلاح خط لوله 10 اينچ موجود كنار گذر فلر بصورت عمودي در مدل نشان داده شود. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | اعمال گردیده است.
4 | فضاي دسترسي بين فنس و آخرين لوله 60 سانت در نظر گرفته شود. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | اعمال گردیده است.
5 | انشعاب وشير تخليه درين بين شير دروازه اي و شير ESDV در خطوط لوله ورودي بايستي در قسمت پاييني لوله در ساعت 6 قرار داده شوند. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | در مدل 60 % اعمال گردیده است.
6 | خطوط لوله ورودي و خروجي پمپ تخليه حوضچه بايستي نشان داده شود. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | در مدل 60 % اعمال گردیده است.
7 | خط لوله آب موجود كنار حوضچه و جاده بايستي نشان داده شود. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | در مدل 60 % اعمال گردیده است.
8 | پله ها و پايه هاي پلتفرم هاي دسترسي بايستي نشان داده شود. |  | BK-SUR-ENG-PIP-01-03935 | 2022-04-16 | در مدل 60 % اعمال گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 16/04/2022 |  |  |  |  | Date: 16/04/2022