## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-CV-PY-0004 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1479 |  |  | Transmital Date:10/11/2022
Document Title:Plant Clean Water Drainage System Layout & Details |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-CV-TR-1479 |  |  | Transmital Date:10/11/2022
[5 empty] | CRS No:NISOC-CRS - D01-BK-GCS-PEDCO-120-CV-PY-0004 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درپاسخ به بند 1 از Clarification By EPC Contractor به اطلاع میرساند همانگونه که از نام مدرک بر می آید و پیرو برگزاری جلسه تله کنفرانس با طراح محترم آن پیمانکار در تاریخ 1401/07/25 مقتضی است جزئیات کامل در نقشه نمایش داده شود. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
2 | درپاسخ به بند 3 از Clarification By EPC Contractor میتوان به جاده، پل، پوشش دیچ آبهای آلوده، پلت فرم و ... اشاره نمود. لذا تکمیل گردد. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
3 | بند 9 از نامه شماره 101255 مورخ 1401/03/24 در نقشه اعمال گردد. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
4 | با عنایت به عنوان مدرک مقتضی است صرفا کانال مربوط به جمع آوری ابهای سطحی در این مدرک لحاظ شده و کانال جمع آوری آبهای آلوده در مدرک مختص خود نمایش داده شود. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
5 | مقتضی است کلیه کانالهای موجود با هاشور متناسب نمایش داده شده و از قسمتهای جدید به نحو مقتضی متمایز گردد. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
6 | مقتضی است جهت هریک از کانالهای جدید -با رعایت رقوم ارتفاعی کانالهای موجود در محل اتصال - مختصات نقاط شروع و پایان ، شیب طولی کانال ، تایپ کانال ارائه گردد. |  | 1401-2294-284599 | 1401/08/07 | نقطه نظر کارفرمای محترم به نحو مقتضی اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: