## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-PI-LI-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1670 |  |  | Transmital Date:10-Dec-2022
Document Title: PIPING SUPPORT LIST - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1670 |  |  | Transmital Date:10-Dec-2022
[5 empty] | CRS No:CRS-BK-W028-PEDCO-110-PI-LI-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک مذکور می بایست پس از تدوین و نهایی شدن تمامی مدارک مهندسی تفصیلی همچون مشخصات فنی متریال ، مدل سه بعدی ، نقشه های ایزومتریک و ... تولید گردد. لذا از آنجاییکه مدارک پیش گفته شده هنوز نهایی نشده اند ، صحه کذاری این مدرک به احاظ جنس متریال و مشخصات فنی در شرایط کنونی از طرف این امور میسر نیست. |  | 1401/2294-368956 | 1401/09/29 | '- این مدرک لیست ساپورت لوله ها (و نه خود لوله های فرآیندی) است و متریال آن C.S. می باشد. - مدل سه بعدی 60% ارائه و نهایی شده است.
2 | با توجه به اینکه مسئولیت کامل طراحی تفصیلی پروژه جز تعهدات پیمانکاراست ، لذا این مدرک می بایست با وضعیت IFI ارسال گردد. |  | 1401/2294-368956 | 1401/09/29 | اعمال گردید.
3 | مزید تاکید می گردد مسئولیت کامل عدم تطابق مشخصات فنی و تعداد اقلام صدرالذکر برعهده آن پیمانکار می باشد. |  | 1401/2294-368956 | 1401/09/29 | مورد قبول است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 11-Apr-2022 |  |  |  |  | Date: 11-Apr-2022