## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-PI-LI-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1670 |  |  | Transmital Date:10-Dec-2022
Document Title: Piping Support List-W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1670 |  |  | Transmital Date:10-Dec-2022
[5 empty] | CRS No:PEDCO-BK-W028-PEDCO-110-PI-LI-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرك PIPING PLAN چاه شماره W028 كه با ترانسميتال T-1628 ارسال شده فقط چند ساپورت اول نشان داده شده و بقيه ساپورتها در آن مدرك نشان داده نشده است كه كامنتهاي لازم در آن مدرك قيد شده لازم به ذكر مي باشد مبناي ساپورت ليست بايستي براساس مدل PDMS و گزارش تحليل تنش و آيزومتريك و PIPING PLAN باشد كه اين مدارك هنوز نهايي نشده اند. لذا ساپورت ليست بايستي پس از نهايي شدن مدارك ذكر شده ارسال گردد. اين مدرك بايستي همراه نقشه اي كه نشان دهنده محل ساپورتها با تگ آنها مي باشد ارائه گردد. |  | BK-SUR-ENG-PIP-01-06450 | 2022-12-20 | همانطوریکه مستحضرید آنالیز تنش در بسته های سرچاهی انجام نمی گردد. مدل 60% سه بعدی نیز ارائه گردیده است . این لیست براساس نقشه استاندارد و براساس مدل انجام شده می باشد و مطابق مدرک isometric drawing بوده و مغایرتی با مدرک Piping Plan ندارد. متریال آن نیز کربن استیل می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 19.Dec.2022 |  |  |  |  | Date: 19.Dec.2022