## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1481 |  |  | Transmital Date: 11/OCT/2022
Document Title: Specification For Air Cooled Heat Exchangers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0110-ME-TR-1481 |  |  | Transmital Date: 11/OCT/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به ارجاع این مدرک به استاندارد IPS ضروری است کلیه موارد غیر مرتبط و تکراری از مدرک حذف گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
2 | با توجه به بند فوق مطالبی که عینا مطابق با استاندارد در مدرک بیان شده است حذف گردد. به عنوان نمونه بند 4 و 8 و 1 و 7 تکراری است. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
3 | شماره مدارک P&ID ذکر شده در مدرک درج گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
4 | با توجه به اینکه مدرک فوق به استاندارد IPS-G-Me-245 ارجاع شده است، لذا ضروریست موارد غیر مرتبط از مدرک حذف گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
5 | ساختار و تعاریف مربوط به صفحه 4 مدرک مطابق با دیگر مدارک اصلاح گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
6 | به جای کلمه Company از Client استفاده گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
7 | بخش 3.5 مطابق با دیگر مدارک تهیه گردد. |  | 01/2294/325717 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 01/04/2023