## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1084 |  |  | Transmital Date: 18 Jun 2022
Document Title: Data Sheets For WHCP/HPU - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1084 |  |  | Transmital Date: 18 Jun 2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص موارد REPLY SHEET نظر خاصی نمی باشد. |  | 01/2294/194443 | 1401/06/03 | -
2 | عطف به نامه 172884 مورخ 1401/05/20 اظهار نظر در خصوص اطلاعات فرآیندی مدرک فوق منوط به نهایی سازی موارد ذکر شده در نامه مذکور می باشد. |  | 01/2294/194443 | 1401/06/03 | اطلاعات فرآيندي مربوط به SSV و SSSV مطابق نامه به شماره" س ط ب/10015 "به تاریخ 1401/05/09 اصلاح و بروز رسانی گردید.
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 25 Jul 2022 |  |  |  |  | Date: