## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1084 |  |  | Transmital Date: 18 Jun 2022
Document Title: Data Sheets For WHCP/HPU - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1084 |  |  | Transmital Date: 18 Jun 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرآيندي مربوط به SSV و SSSV طبق آخرين اطلاعات ارسال شده تكميل گردد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | اطلاعات فرآيندي مربوط به SSV و SSSV مطابق نامه به شماره" س ط ب/10015 "به تاریخ 1401/05/09 اصلاح و بروز رسانی گردید.
2 | در مدرك return line و Quick exhaust Valve براي لاين SSV ديده شود. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مطابق خواست کارفرمای محترم به مدرک اضافه گردید.
3 | موارد بر اساس آخرين نقطه نظرات تاييد شده توسط كارفرما در صورتجلسه PIM و KOM مربوط به WHCP برگزار شده در شركت كاردانان شرق در تاريخ 26/04/1401 نهايي گردد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مدرک بر اساس آخرين نقطه نظرات تاييد شده توسط كارفرما در صورتجلسه PIM و KOM مربوط به WHCP برگزار شده در شركت كاردانان شرق در تاريخ 1401/04/26 اصلاح و نهايي گردید.
4 | اطلاعات فرآيندي و setpoint ها براي pressure switch ها مجددا بررسي و نهايي گردد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مدرک مطابق آخرین نسخه از مدارک مرجع اصلاح و بروز رسانی گردید.
5 | فرآيند: بنظر مي رسد فشار عملياتي نياز به بازنگري دارد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مطابق اصلاح و بروز رسانی گردید.
6 | فرآيند: تصميم هاي اتخاذ شده در جلسه SIL در خصوص نقطه تنظيم سوييچ PSHH-1101 B و سويچ هاي مشابه در مدرك اعمال گردد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مطابق اصلاح و بروز رسانی گردید.
7 | فرآيند: نهايي سازي نقطه تنظيم ساير سوييچ ها پس از دريافت اطلاعات از ذينفع اصلي ميسر مي باشد. |  | BK-SUR-ENG-INS-01-05236 | 2022-07-25 | مطابق اصلاح و بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 25 Jul 2022 |  |  |  |  | Date: