## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-SP-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0748 |  |  | Transmital Date: 27 Mar 2022
Document Title: Specification For WHCP/HPU |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0748 |  |  | Transmital Date: 27 Mar 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-SP-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدارك مربوط به اين مدرك هنوز نهايي نشده است، لذا در صورت تغيير در هركدام از مدارك مربوطه، لازم است اين مدرك نيز بروز رساني شود. |  | BK-SUR-ENG-INS-01-03940 | 2022-04-16 | مدرک مطابق آخرین نسخه از مدارک مرجع اصلاح و بروز رسانی گردید.
2 | در اين برهه و با توجه به مفاد ماده 13 شرايط عمومي پيمان، نظر خاصي مطرح نمي باشد. |  | BK-SUR-ENG-INS-01-03940 | 2022-04-16 | -
3 | با توجه به اينكه ديتا هاي فرآيندي مانند SSVو SSSV نهايي نشده است در صورت نهايي سازي تغييرات در مدرك مربوطه لحاظ و مدرك به روز رساني گردد. |  | BK-SUR-ENG-INS-01-03940 | 2022-04-16 | اطلاعات فرآيندي مربوط به SSV و SSSV مطابق نامه به شماره" س ط ب/10015 "به تاریخ 1401/05/09 اصلاح و بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Apr 2022 |  |  |  |  | Date: