## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0026 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1586 |  |  | Transmital Date: 11/14/2022
Document Title: Process Data Sheets For Potable Water Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1586 |  |  | Transmital Date: 11/14/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0026_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برخی اطلاعات درج شده در مدرک با آخرین ویرایش مدرک P&ID پروژه همخوان نبوده و ضروری است همسان سازی گردد. به عنوان نمونه میزان اختلاف فشار در داده برگ و P&ID یکسان نمی باشد. |  | 1401-2294-375024 | 1401/10/04 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: