## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0008-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1279 |  |  | Transmital Date: 16-Aug-2022
Document Title: Calculation note for diesel generator sizing of well pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-EL-TR-1279 |  |  | Transmital Date: 16-Aug-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0008-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند5.2: پاراگراف آخر که منجر به نتیجه گیری توان 132KW شده از مدرک حذف گردد. |  | 1401-2294-205604 | 1401-06-09 | حذف گردید.
2 | لازم است که محاسبات دیزل و dip ولتاژ زنراتور پس از تعیین سازنده و براساس نمودار های دیزل ژنراتور منتخب مورد بازبینی و اصلاح قرار گرفته، و جهت بررسی به این امور ارسال گردد. در این خصوص لازم است که NOTE آخر مدرک بر این اساس اصلاح گردد. |  | 1401-2294-205604 | 1401-06-09 | مدرک محاسباتی بعد از عقد قرارداد با سازنده اصلی و تولید محاسبات جدید توسط ایشان، ویرایش خواهد شد و نمودارهای دیزل ژنراتور در نظر گرفته شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 24-Aug-2022 |  |  |  |  | Date: