## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1466 |  |  | Transmital Date:10/9/2022
Document Title:Process Flow Diagram (PFD) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1466 |  |  | Transmital Date:10/9/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ضروریست در هر مقطع یکسانسازی مدارک با "PFD" و "PID " و بر عکس رخ دهد به عنوان مثال در Normal Capacity مربوط به TK-2102 و عدم یکسانسازی آن با مدرک Calculation Note For Drum و یا به توپکگیرهای PR-101,102 در ورودی ایستگاه با آخرین مدرک PID اشاره کرد لذا ضروریست این مهم مورد بررسی مجدد آن پیمانکار قرار گیرد. |  | 1401-2294-378378 | 1401/10/06 | اصلاح گردید.
1 | در خصوص مدرک توپکران PL-3101 در خروجی ایستگاه به سیاه مکان ضروریست آن پیمانکار نام و شرایط فرآیندی را با آخرین ویرایش مدرک PFD(PPL) مطابقت و مورد بررسی مجدد و اصلاح قرار دهد. |  | 1401-2294-378378 | 1401/10/06 | شرایط فرآیندی توپکران PL-3101 با توجه به استریم 15 جداول H&M اصلاح گردید. لازم به ذکر است دلیل اختلاف ناچیز در فشار PFD(PPL) در سناریو زمستان با PFD(GCS) به دلیل نحوه محاسبه فشار به وسیله دو نرم افزار مختلف HYSYS و OLGA می باشد. در PFD(PPL) فشار بوسیله نرم افزار OLGA ودر PFD(GCS) دما بوسیله نرم افزار HYSYS محاسبه شده است. لازم به ذکر است در سناریو تابستان شرایط فرآیندی در و PFD(GCS) و PFD(PPL) یکسان می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: