## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1466 |  |  | Transmital Date:10/9/2022
Document Title:Process Flow Diagram (PFD) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1466 |  |  | Transmital Date:10/9/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PF-0001 _D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقاط تزریق موادشیمیایی، در نقشه PFD مشخص گردد. |  | BK-SUR-ENG-PCS-01-05973 | 2022-10-25 | نقاط تزریق CORROSION INHIBITOR در مدرک MFD نمایش داده شده است. لازم بهذکر است با توجه به اینکه تزریق متانول به صورت غیرپیوسته می باشد لذا از منظر این پیمانکار نمایش آنه در مدرک فوق الزام آور نمی باشد.
2 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-05973 | 2022-10-25 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: