## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-DT-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1580 |  |  | Transmital Date: 11/7/2022
Document Title:Process Data Sheets For 2nd Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1580 |  |  | Transmital Date: 11/7/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0005_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه می شود از طول Bundle های استاندارد مندرج در IPS-E-PR-780، برای سایزینگ استفاده شود |  | BK-SUR-ENG-PCS-01-06241 | 2022-11-22 | طول Bundle ها بر اساس استاندارد IPS-G-ME-245 اصلاح گردید.
2 | در خصوص حداکثر دمای قابل قبول برای هوای خروجی، مطابق با نظر ذینفع اصلی پروژه عمل شود. |  | BK-SUR-ENG-PCS-01-06241 | 2022-11-22 | مورد تایید است.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06241 | 2022-11-22 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021