## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-SA-PY-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1060 |  |  | Transmital Date:11-JUN-2022
Document Title: Safety & Fire Fighting Equipment Location Layout - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-EL-TR-1060 |  |  | Transmital Date:11-JUN-2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-SA-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است نقشه جانمایی تجهیزات ایمنی مربوط به ساختمانها به این نقشه اضافه گردد. |  | 1401-2294-171063 | 1401-05-18 | صفحات 2 و 3 این مدرک مربوط به جانمایی ادوات ایمنی می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 17-Jul-2022 |  |  |  |  | Date: