## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0003_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1477 |  |  | Transmital Date: 18/10/2022
Document Title: Mechanical Data Sheets For 1st Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-1477 |  |  | Transmital Date: 18/10/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0003_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به شرایط پروژه انجام تست HIC/SCC الزامی است. لذا ضروری است لزوم انجام آن در مدرک درج گردد. |  | 01/2294/325678 | 1401/09/02 | تست های مذکور بر روی متریال S.S 316L موضوعیت ندارد.
2 | در یادداشت 5 به انجام تست مطابق با ITP اشاره شود. همچنین در دستورالعمل مربوطه می بایست به تایید کارفرما برسد. |  | 01/2294/325678 | 1401/09/02 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 10/18/2022 |  |  |  |  | Date: 1/10/2023