## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0005_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1469 |  |  | Transmital Date:09/October/2022
Document Title:Mechanical Data Sheets For 2nd Stage Gas Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-1469 |  |  | Transmital Date:09/October/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0005_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Electrical comments
1 | با توجه به عدم ارائه دلایل کافی در Reply Sheet ضروری است نوع Fin در مدرک به صورت VTA قید شده و در مراحل خرید بررسی گردد. |  | 01/2294/367289 | 1401/09/29 | نظر کارفرمای محترم اعمال گردید. (نوع فین مشخص نشده بود و بر عهده وندور است.)
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 10/18/2022 |  |  |  |  | Date: 1/10/2023