## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-LI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0598 |  |  | Transmital Date: 16/02/2022
Document Title: Line List |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0598 |  |  | Transmital Date: 16/02/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-LI-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه BK-PEDCO-NISOC-0011-PR-LT-25792 مورخ 1400/11/27 (شماره سیستمی 32632)با موضوع صدرالذکر ، در خصوص مدرک پیوست به ترنسمیتال صدرالذکر در این مقطع نظر خاصی مطرح نیست لیکن با توجه به عدم نهایی شدن مدارک PFD , P&ID می بایست هرگونه تغییرات مدارک مزبور در این مدرک نیز منعکس گردد. |  | 1400-2294-443211 | 1400/12/19 | مورد تایید است . این مدرک بر اساس آخرین ویرایش ارسال شده از PFDوPID می باشد .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021