## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1448 |  |  | Transmital Date: 10/2/2022
Document Title: Process Flow Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1448 |  |  | Transmital Date:10/2/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص ردیف یک و دو ضروریست میزان water cut , viscosity درج گردد لذا آن پیمانکار در این مقطع میتواند انتشار نسخ سخت با درج مهر AFC همراه با اصلاحات بیان شده را جهت پیشبرد در مهندسی به این امور ارائه نماید . |  | 1401-2294-312894 | 1401/08/24 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: | Signature
| Date: 30/04/2022 |  |  |  |  | Date: