## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-PF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1448 |  |  | Transmital Date: 10/2/2022
Document Title: Process Flow Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1448 |  |  | Transmital Date:10/2/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-PF-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم تطابق ترکیب درصد جریان شماره 13 با فایل شبیه سازی ارائه شده به پیوست مدرک Simulation Report، توضیحات تکمیلی در خصوص حالت عملیاتی فرض شده برای ترکیب درصد جریان شماره 13، به صورت Note در مدرک درج شده و فایل شبیه سازی مرتبط با آن به پیوست ارسال گردد. |  | BK-SUR-ENG-PCS-01-05944 | 2022-10-22 | جریان شماره 13 با توجه به فایل پیوست ارسال شده ، اصلاح شده است و در بخش H&M میزان ترکیب درصد جریان 13 و شرایط عملیاتی آن ، آورده شده است .
2 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-05944 | 2022-10-22 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: | Signature
| Date: 30/04/2022 |  |  |  |  | Date: