## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-PY-0013_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1526 |  |  | Transmital Date: 22-Oct-2022
Document Title: Cable Route layout for Production Unit |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-EL-TR-1526 |  |  | Transmital Date: 22-Oct-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-PY-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عمق ترانشه کابل حداقل 0.8 متر در نظر گرفته شود. |  | 1401-2294-325600 | 1401-09-02 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Sadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 05-Nov-2022 |  |  |  |  | Date: