## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0006_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1362 |  |  | Transmital Date: 5 Sep 2022
Document Title: Control System Loop Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1362 |  |  | Transmital Date: 5 Sep 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19 | ملاحظه شد.
2 | اين مدرك با PID تناقض دارد. در خصوص لاجيك مربوط به HIC-1701X كه در مدرك P&ID وجود دارد، شفاف سازي شود. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19
3 | آلارم High و Low براي ترانسيمترها (در صورت وجود در مدرك P&ID) در قسمت Operation Display مشخص شود. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19 | سطوح الارم ها در مدرک Logic Diagram و Alarm set point list بطور کامل مشخص هست. از آنجایی که این تنظیمات در سیستم کنترل انجام خواهد شد، و در مسیر لوپ تاثیری نخواهد داشت، در این مدرک آورده نشده است.
4 | موارد HOLD مشخص شود. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19
5 | نسخه مدارك مشخص شود. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19
6 | Tag ادوات ابزاردقيق، با مدرك P&ID مانند FIT-1702X تناقض دارد. تمامي تگ ها مجددا بررسي گردد. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19
7 | با توجه به اينكه مدارك پيش نياز نهايي نيست، موارد در صورت تغيير در اين مدرك منعكس شود. |  | BK-SUR-ENG-INS-01-05716 | 2022-09-19 | این مدرک بر اساس آخرین نسخه P&ID تهیه شده است. بدیهی است در صورت تغيير در مدارک پایه، کلیه مدارک به روز رسانی خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 19 Sep 2022 |  |  |  |  | Date: