## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-SA-PY-00011_D00 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-0715 |  |  | Transmital Date:12/MAR/2022
Document Title:Hazardous Area Classification Layout - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-TR-0715 |  |  | Transmital Date:12/MAR/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-SA-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در قسمت Notes ،طبقه بندی منطقه خطر مربوط به اتصالات ،ولوها و... ذکر گردد. |  | 1401-2294-16831 | 1401/01/21 | اعمال گردید. ( نوت 3)
2 | طیقه بندی منطقه خطر پمپ به مدرک اضافه گردد . |  | 1401-2294-16831 | 1401/01/21 | تغییرات اعمال گردید.
3 | نمای جانبی طبقه بندی منطقه خطر تجهیزات بر اساس استاندارد API-RP-505 به مدرک اضافه گردد. |  | 1401-2294-16831 | 1401/01/21 | تغییرات اعمال گردید.
4 | نقطه نظرات این امور در خصوص مدرک Hazard Source List ،در این مدرک اعمال گردد.پیشنهاد می شود پس از نهایی شدن مدرک Hazard Source List ،مدرک فوق جهت بررسی به ابن امور ارسال گردد . |  | 1401-2294-16831 | 1401/01/21 | با توجه به اعمال کامنت و ارسال مدرک hazard source list پیش از مدرک حاضر, تمام کامنت های مربوطه در ویرایش جدید اعمال گردیده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: