## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0005_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1690 |  |  | Transmital Date: 12 Dec 2022
Document Title: PMR For Control Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1690 |  |  | Transmital Date: 12 Dec 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0005_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Note مربوط به سایز کنترل ولو ها در مدرک finalized by vendor and client agreement اصلاح گردد . |  | 01/2294/375939 | 1401/10/04 | مطابق نظرکارفرمای محترم اضافه شد.
2 | جدول تجهیزات بجای قسمت جنرال مناسب است در قسمت Scope of supply آورده شود. |  | 01/2294/375939 | 1401/10/04 | مطابق نظرکارفرمای محترم اصلاح شد.
3 | خدمات پس از فروش حد اقل 10 سال در نظر گرفته شود. |  | 01/2294/375939 | 1401/10/04 | مطابق نظرکارفرمای محترم اصلاح شد.
4 | در مدارک پیوست به چه علت سه ویرایش از نقشه های P&ID آورده شده است ؟ ویرایش نهایی ( آخرین ویرایش) مدارک ملاک عمل می باشد. |  | 01/2294/375939 | 1401/10/04 | مطابق نظرکارفرمای محترم اصلاح شد.
5 | در متن مدارک قبل از قسمت پیوستها قید گردد، آخرین نسخه مدارک پیوست ( نسخه نهایی) ملاک عمل میباشد. |  | 01/2294/375939 | 1401/10/04 | مطابق نظرکارفرمای محترم اصلاح شد.
5 | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد ماقصه ، استاندارد های IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمیباشد. |  | 01/2294/375939 | 1401/10/04 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date:26 Dec 2022 |  |  |  |  | Date: