## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-PI-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1584 |  |  | Transmital Date: 12 Nov 2022
Document Title: Plot Plan Drawing - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1584 |  |  | Transmital Date: 12 Nov 2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مختصات جغرافیایی تمام نقاط مورد اشاره در این مدرک می بایست به UTM تغییر یابد. همچنین تراز های ارتفاعی FGL - RGL و ... نیز به همین ترتیب اصلاح گردند. |  | 01/2294/354063 | 1401/09/20 | احتراما با توجه به ملاک قرار گرفتن مدرک PLOT PLAN در مدل سازی سه بعدی و نیاز به LOCAL بودن مختصات در مدل سازی؛ در مدارک PLOT PLAN امکان استفاده از مختصات UTM نمی باشد
2 | عرض جاده سواره رو گودال سوخت و لوکیشن - 6 متر- در نقشه درج گردد. |  | 01/2294/354063 | 1401/09/20 | احتراما نقطه نظر اعمال گردید.
3 | طول جاده دسترسی گودال سوخت به میزان 10 متر افزایش داده شده که تبعات هر گونه تغییر بر عهده و مسئولیت پیمانکار بوده و کارفرما هیچ ادعایی را نمی پذیرد. |  | 01/2294/354063 | 1401/09/20 | احتراما نقطه نظر مدنظر قرار داده می شود.
4 | محل شماره 16 از نقشه حذف گردد. |  | 01/2294/354063 | 1401/09/20 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: G.Khisravizadegan F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26-Nov-2022 |  |  |  |  | Date: 26-Nov-2022