## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-SA-PY-0004-D01 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-0943 |  |  | Transmital Date:14/MAY/2022
Document Title: Safety & Fire Fighting Equipment Location Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-TR-0943 |  |  | Transmital Date:14/MAY/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0004-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک Safety & Fire Fighting Equipment Location Layout مورد مطالعه و بررسی قرار گرفت و با توجه به وضوح پایین نقشه ها ی پیوست ،مدرک قابل بررسی نمی باشد. |  | 1401-2294-176982 | 1401/05/23 | نقشه های اصلاح شده بر اساس اخرین ویرایش Plot Plan ،جهت بررسی به حضور ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: