## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-MR-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1188 |  |  | Transmital Date: 24/Jul/2022
Document Title: PMR For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-1188 |  |  | Transmital Date:
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-ME-MR-0001-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 00/2294/440957 بیان گردید مدارک PMR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه (مانند مشخصات فنی، داده برگ ها، PMS، MTOو ...) می بایست تولید گردد، چرا که تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج عنوان آن در متن، ضمیمه PMR ها شوند. از آنجایی که مدارک مهندسی مرتبط تا کنون نهایی نشده اند، بدیهی است در صورت پیشبرد فاز مهندسی خرید براساس ویرایش اولیه مدارک تولید شده، مسئولیت بروز رسانی کلیه اختلافات و عدم تطابق ها بر عهده پیمانکار خواهد بود. |  | 01/2294/183487 | 18/08/2022 | با توجه به عدم اخذ نقطه نظر جدید بر مدارک ضمیمه MR مانند داده برگ فنی مربوط به تله دریافت و ارسال توپک، لذا از کارفرمای محترم خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: