## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-MR-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1188 |  |  | Transmital Date: 24/Jul/2022
Document Title: PMR For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-1188 |  |  | Transmital Date:
[5 empty] | CRS No:PEDCO-CRS-BK-PPL-PEDCO-320-ME-MR-0001-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5: 1-عبارت "Project ITP Procedure" به "دستورالعمل بازرسي خريد و ساخت كالا" به شماره مدرك ICE-EID-MI-SP01-Rev.01 تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05344 | 2022-08-03 | عبارت اضافه شد و دستورالعمل در لیست مدارک پیوست 2 موجود می باشد. |  |  | See Item 4
2 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل FDB Requirements اضافه گردد. |  | BK-SUR-ENG-MEC-01-05344 | 2022-08-03 | نقطه نظر ارایه شده اعمال شد. |  |  | Closed
3 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachmen 2" حذف گردد. 2. عبارت "List of Documents will be Finalized in Vendor Document Index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-MEC-01-05344 | 2022-08-03 | نقطه نظرات ارایه شده اعمال شد. |  |  | Closed
4 | در بند 6 : عبارت "QC Plan" به "ITP" تغيير يافته و دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 به عنوان رفرنس تهيه مدرك ITP اضافه شده و دستورالعمل فوق در ليست مدارك پيوست 1 آورده شود. |  | BK-SUR-ENG-MEC-01-05344 | 2022-08-03 | نقطه نظرات ارایه شده اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: 8/3/2022