## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1368 |  |  | Transmital Date: 06.Sep.2022
Document Title: Chemical Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1368 |  |  | Transmital Date: 06.Sep.2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است در کل مدرک نام توپگیر PR-2102 بر اساس آخرین ویرایش P&ID به PR-2002 اصلاح گردد. |  | 01/2294/318022 | 1401/08/28 | اصلاح گردید.
2 | با توجه به موارد ذکر شده در جدول شماره 2 مدرک، خروجی V-2102، خروجی پکیج نم‌زدایی PK-2101 و Gas Pipeline، خط جریانی متانول در مدرک P&ID در نظر گرفته نشده است. ضروریست توضیحات پیمانکار ارائه گردد. |  | 01/2294/318022 | 1401/08/28 | در مدرک PID اصلاح می گردد.
3 | علت افزایش میزان مصارف متانول نسبت به نسخه قبلی مدرک ارائه گردد. |  | 01/2294/318022 | 1401/08/28 | بر اساس به روز رسانی محاسبات تشکیل هیدرات در ویرایش قبلی مدرک فوق که به شرح پیوست به آن کارفرمای محترم ارسال گردید،مصارف متانول اصلاح گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021